## Functional SRS
Functional SRS — Work Distribution Schedule (March – June 2026)
SRS ID | Feature / Module | Sub Tasks | Mar'26 |  |  |  | Apr'26 |  |  |  | May'26 |  |  |  | Jun'26
|  |  | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4
SRS-001 | Real-Time Dashboard & Monitoring | Dashboard UI, status indicators, filtering
SRS-002 | PC Details & Administration | PC detail views, metadata editing
SRS-003 | PC Model & Config Operations | Upload/download/change models & configs
SRS-004 | Model Library & Distribution | Library page, distribution pipeline
SRS-005 | Model Editor & XML Visual Editor | Code editor, XML param editor, diff view
SRS-006 | Version History & Rollback | Auto-versioning, diff viewer, revert
SRS-007 | Log Analyser & Visualization | Log parsing, Gantt charts, images
SRS-008 | Agent Registration & Heartbeat | Registration dialog, heartbeat loop
SRS-009 | Agent Sync Operations | Model/config/log sync, image upload
SRS-010 | UI Framework & Navigation | Sidebar, themes, routing, 404 page

## Non-Functional SRS
Non-Functional SRS — Work Distribution Schedule (March – June 2026)
SRS ID | Feature / Module | Sub Tasks | Mar'26 |  |  |  | Apr'26 |  |  |  | May'26 |  |  |  | Jun'26
|  |  | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4
NFR-001 | Performance & Reliability | Load time, caching, timeouts, offline detection
NFR-002 | Usability & Security | Themes, color-coding, path validation